## Sheet1
Log_Date | Discipline | Equipment_Tag | Work_Description | Site_Area | Status | Quantity | UOM | Vendor | Remarks
2026-08-21 | civil | TK-101 | Excavation for tank ring wall foundation | Offsite Tank Farm | finish | 450 | cum | Tata Projects | Excavation completed to -3.5m depth
2026-08-21 | civil | P-201A | M30 concrete pouring for pump foundation | Pump Bay 4 | start | 85 | cum | Bridge & Roof | Concrete pouring started at 09:00 hrs
2026-08-21 | civil | C-301 | Rebar tying and shuttering for compressor plinth | Compressor House | finish | 15.5 | MT | L&T Civil | Shuttering approved by QA/QC
2026-08-22 | civil | CT-04 | RCC Cable Trench excavation | Substation Road | progress | 30 | meters | Punj Lloyd | Delayed due to unmapped utility line crossing
2026-08-22 | civil | PR-05 | Structural steel column erection | Main Pipe Corridor | start | 12 | MT | Tata Projects | First 4 portal frames erected